## Sheet1
ID | Task Name | Start | Finish | Duration | September | [29 empty] | October | [30 empty] | November
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Preview Existing system | 2014-09-01 | 2014-09-14 | 14d | bar: September 1 to September 14
2 | Problem Definition | 2014-09-15 | 2014-09-19 | 5d | bar: September 15 to September 19
3 | High Level Requirements | 2014-09-20 | 2014-09-22 | 3d | bar: September 20 to September 22
4 | Alternative Solutions | 2014-09-23 | 2014-09-23 | 1d | bar: September 23
5 | Requirement Elicitation | 2014-09-24 | 2014-09-29 | 5d | bar: September 24 to September 28
6 | Requirement Analysis | 2014-09-29 | 2014-09-30 | 3d | bar: September 28 to September 30
7 | Milestone: System Analysis | 2014-09-30 | 2014-09-30 | 0d | bar: September 30
8 | Database Changes | 2014-10-01 | 2014-10-15 | 15d | bar: October 1 to October 15
9 | Populate Database | 2014-10-08 | 2014-10-16 | 8d | bar: October 8 to October 16
10 | Modify System Architecture | 2014-10-01 | 2014-10-31 | 31d | bar: October 1 to October 31
11 | UI Form Modifications | 2014-10-21 | 2014-10-31 | 10d | bar: October 21 to October 31
12 | UI Flowchart Creation | 2014-10-17 | 2014-10-31 | 14d | bar: October 17 to October 31
13 | Implement Functions | 2014-10-23 | 2014-11-03 | 11d | bar: October 24 to November 3
14 | Initial Testing
15 | Milestone: Implemention
16 | Finalize Implementation
17 | Complete Functional Tests
18 | Evaluate Test Results
19 | Documentation
20 | Milestone: System Complete